## Slide 1: Systems Analysis and Design 11th Edition
Chapter 3
Managing Systems Projects

## Slide 2: Chapter Objectives
Explain project planning, scheduling, monitoring, and reporting
Draw a project triangle that shows the relationship among project cost, scope, and time
Create a work breakdown structure, identify task patterns, and calculate a critical path
Explain techniques for estimating task completion times and costs
Describe various scheduling tools, including Gantt charts and PERT/CPM charts

## Slide 3: Chapter Objectives (Cont.)
Analyze task dependencies, durations, start dates, and end dates
Describe project management software and how it can be of assistance
Control and manage project changes as they occur
Discuss the importance of managing project risks
Understand why projects sometimes fail

## Slide 4: Overview of Project Management
Project Management: Planning, scheduling, monitoring and controlling, and reporting on information system development
What Shapes a Project?
  Successful projects must be completed on time, within budget, meet requirements, and satisfy users
What Is a Project Triangle?
  Challenge – To find optimal balance among the factors
    Any change in one leg of the triangle will affect the other legs
FIGURE 3-2 A typical project triangle includes cost, scope, and time.

## Slide 5: Overview of Project Management (Cont.)
What Does a Project Manager Do?
  Project planning: Identifying all project tasks and estimating the completion time and cost of each
  Project scheduling: Creating a specific timetable showing tasks, task dependencies, and critical tasks that might delay the project
  Project monitoring: Guiding, supervising, and coordinating the project team’s workload
  Project reporting: Creating regular progress reports for management, users, and the project team itself

## Slide 6: Creating a Work Breakdown Structure
Work breakdown structure (WBS): Breaking down a project into a series of smaller tasks
Gantt Chart
  A horizontal bar chart representing a set of tasks
  Shows planned and actual progress on a project
  Simplifies complex projects using a task group
FIGURE 3-3 In this Gantt chart, notice the yellow bars that show the percentage of task completion.

## Slide 7: Creating a Work Breakdown Structure (Cont. 1)
PERT/CPM Charts
  Program Evaluation Review Technique (PERT)
    Developed by the U.S. Navy to manage complex projects
  Critical Path Method (CPM)
    Developed by private industry
  Utilizes a bottom-up technique
  Useful for scheduling, monitoring, and controlling actual work
    Displays complex task patterns and relationships

## Slide 8: Creating a Work Breakdown Structure (Cont. 2)
FIGURE 3-4 The top screen shows a Gantt chart with six tasks. The PERT chart in the bottom screen displays an easy-to-follow task pattern for the same project. When the user mouses over the summary box for Task 5, the details become visible.

## Slide 9: Creating a Work Breakdown Structure (Cont. 3)
Identifying Tasks in a WBS
  Task or activity: Any work that has a beginning and an end
    Requires the use of company resources such as people, time, or money
    Should be small and manageable
  Projects have events or milestones
    Events or milestones: Recognizable reference points used to monitor progress

## Slide 10: Creating a Work Breakdown Structure (Cont. 4)
FIGURE 3-5 Using a questionnaire requires a series of tasks and events to track the progress. The illustration shows the relationship between the tasks and the events, or milestones, that mark the beginning and end of each task.

## Slide 11: Creating a Work Breakdown Structure (Cont. 5)
Identifying Tasks in a Work Breakdown Structure (WBS)
  Listing the tasks
  Estimating task duration - Can be hours, days, or weeks
    Time estimates made by project managers
      Best case-estimate (B), probable-case estimate (P), and worst-case estimate (W)
    After making estimates, the manager assigns a weight to each estimate and calculates the task duration

## Slide 12: Creating a Work Breakdown Structure (Cont. 6)
FIGURE 3-7 In this table, columns have been added for task number, description, duration, and predecessor tasks, which must be completed before another task can start.
FIGURE 3-6 The three versions show how to transform a task statement into a list of specific tasks for a work breakdown structure.

## Slide 13: Creating a Work Breakdown Structure (Cont. 7)
Factors Affecting Duration
  Project size
    Identify all project tasks and the time required for each
    Consider time taken for events affecting productivity
  Human resources
    Assemble and guide a development team that has the skill and experience to handle the project
    Deal with factors that could affect the project’s timeline

## Slide 14: Creating a Work Breakdown Structure (Cont. 8)
Factors Affecting Duration
  Experience with similar projects
    Develop time and cost estimates based on the resources used for similar, previously developed information systems
  Constraints
    Define system requirements that can be achieved realistically within the required constraints
      Calculate resources needed in the absence of constraints

## Slide 15: Creating a Work Breakdown Structure (Cont. 9)
FIGURE 3-8 Task durations have been added, and the WBS is complete except for predecessor task information. The predecessor tasks will determine task patterns and sequence of performance.
FIGURE 3-9 This Microsoft Project screen displays the same WBS, including task number, task name, duration, and predecessor tasks.

## Slide 16: Identifying Task Patterns
Task Patterns
  Arrangement of tasks in a logical sequence
  Can involve dependent tasks, multiple successor tasks, and multiple predecessor tasks
Using Task Boxes to Create a Model
FIGURE 3-10 Each section of the task box contains important information about the task, including the Task Name, Task ID, Task Duration, Start Day/Date, and Finish Day/Date.
Notes: Arrangement of tasks in a logical sequence

## Slide 17: Identifying Task Patterns (Cont. 1)
Task Patterns
  Dependent Tasks
    Tasks that need to be completed in a sequence
    One task can be initiated only after the prior task has
    been completed
FIGURE 3-12 This example of a dependent task shows that the finish time of Task 1, Day 5, controls the start date of Task 2, which is Day 6.

## Slide 18: Identifying Task Patterns (Cont. 2)
Task Patterns
  Multiple Successor Tasks
    Tasks that can be
    initiated simultaneously
      Tasks are termed concurrent
    Often, two or more concurrent tasks depend on a predecessor task
FIGURE 3-13 This example of multiple successor tasks shows that the finish time for Task 1 determines the start time for both Tasks 2 and 3.

## Slide 19: Identifying Task Patterns (Cont. 3)
Task Patterns
  Multiple Predecessor Tasks
    When the initiation of
    a task depends on the
    completion of two or
    more prior tasks
FIGURE 3-14 This example of multiple predecessor tasks shows that the start time for a successor task must be the latest (largest) finish time for any of its preceding tasks. In the example shown, Task 1 ends on Day 15, while Task 2 ends on Day 5, so Task 1 controls the start time for Task 3.

## Slide 20: Identifying Task Patterns (Cont. 4)
Identifying Task Patterns
  Words like then, when, or and signal a sequence of events
    Do Task 1, then do Task 2
      Describes dependent tasks that must be completed one after the other
    When Task 2 is finished, start two tasks
      Task 3 and Task 4 describe multiple successor tasks that can both start as soon as Task 2 is finished
    When Tasks 5 and 6 are done, start Task 7
      Indicates that Task 7 is a multiple predecessor task

## Slide 21: Identifying Task Patterns (Cont. 5)
Working with Complex Task Patterns
  Study the facts very carefully to understand the logic and sequence of task patterns
  Schedule will be wrong if task patterns are incorrect
FIGURE 3-15 Dependent tasks
FIGURE 3-16 Dependent tasks and multiple successor tasks
FIGURE 3-17 Dependent tasks, multiple successor tasks, and multiple predecessor tasks

## Slide 22: Calculating the Critical Path
Critical Path: Series of tasks which, if delayed, will affect the completion date of the overall project
  If any task on the critical path falls behind schedule, the entire project will be delayed
Calculating the Critical Path
  Review patterns
  Determine start and finish dates, which will define the critical path

## Slide 23: Calculating the Critical Path (Cont. 1)
FIGURE 3-18 Example of a PERT/CPM chart with five tasks. Task 2 is a dependent task that has multiple successor tasks. Task 5 has multiple predecessor tasks. In this figure, the analyst has arranged the tasks and entered task names, IDs, and durations.

## Slide 24: Calculating the Critical Path (Cont. 2)
FIGURE 3-19 Now the analyst has entered the start and finish times, using the rules explained in this section. Notice that the overall project has a duration of 95 days.

## Slide 25: Project Monitoring and Control
Monitoring and Control Techniques
  Structured walk-through: Review of a project team member’s work by other team members
    Takes place throughout the SDLC
    Known as design, code, or testing reviews based on the phase in which they occur

## Slide 26: Project Monitoring and Control (Cont.)
Maintaining a Schedule
  Most projects run into some problems or delays
  Projects managers monitor and control the work by:
    Anticipating problems, avoiding them, and minimizing their impact
    Identifying potential solutions and selecting the best way to solve the problem

## Slide 27: Reporting
Project Status Meetings
  Project managers schedule regular meetings to share updates, discuss common problems, and explain new techniques
  Help collect data from team members and conduct brainstorming sessions
Project Status Reports
  Regularly communicated by project managers to supervisors, upper management, or users
    Managers must communicate potential problems to the management at the right time

## Slide 28: Project Management Examples
PERT/CPM Examples
  Step 1 - Display the tasks and task patterns
    Identify the tasks
    Determine task dependencies
    Enter the task name, ID, and duration
  Step 2 - Enter start and finish times
    In case of more than one predecessor tasks for a successor task, use the latest finish time of the predecessor tasks to determine the start time for the successor task

## Slide 29: Project Management Examples (Cont. 1)
PERT/CPM Examples
  In case of more than one successor task for the predecessor task, use the predecessor task’s finish time to determine the start time for all successor tasks
  Continuing from left to right, add the task duration for each task to its start time to determine and enter its finish time

## Slide 30: Project Management Examples (Cont. 2)
FIGURE 3-22 To transform a task list into a PERT/CPM chart, you first enter the task name, ID, duration, and predecessors for each task. Notice that this example includes dependent tasks, tasks with multiple successors, and tasks with multiple predecessors.

## Slide 31: Project Management Examples (Cont. 3)
FIGURE 3-23 To complete the PERT/CPM chart, you apply the guidelines explained in this section. For example, Task 1 has a one-day duration, so you enter the start and finish for Task 1 as Day 1. Then you enter Day 2 as the start for successor Tasks 2 and 3.

## Slide 32: Project Management Software
Microsoft Project
  Full-featured program that holds the dominant share of the market
GanttProject
  Free, open source program
Gantter
  Free cloud-based project management tool
Apptivo and smartsheet
  Paid Web-based project management tools

## Slide 33: Project Management Software (Cont. 1)
FIGURE 3-26 Notice how each view displays the project and highlights the critical path. If you were the project manager on September 25, your primary concern should be conducting the user survey.

## Slide 34: Project Management Software (Cont. 2)
FIGURE 3-26 Notice how each view displays the project and highlights the critical path. If you were the project manager on September 25, your primary concern should be conducting the user survey.

## Slide 35: Project Management Software (Cont. 3)
FIGURE 3-26 Notice how each view displays the project and highlights the critical path. If you were the project manager on September 25, your primary concern should be conducting the user survey.

## Slide 36: Risk Management
Steps in Risk Management
  Develop a risk management plan
    Review the project’s scope, stakeholders, budget, schedule, and any other internal or external factors that might affect the project
    Define project roles and responsibilities, risk management methods and procedures, categories of risks, and contingency plans
  Identify the risks
    List each risk and assess the likelihood that it could affect the project

## Slide 37: Risk Management (Cont. 1)
Steps in Risk Management
  Analyze the risks
    Qualitative risk analysis: Evaluates each risk by estimating the probability that it will occur and the degree of impact
    Quantitative risk analysis: Helps understand the actual impact in terms of dollars, time, project scope, or quality
  Create a risk response plan
    Risk response plan: Proactive effort to anticipate a risk and describe an action plan to deal with it
  Monitor risks - Conduct a continuous tracking process

## Slide 38: Risk Management (Cont. 2)
FIGURE 3-29 You can use a Microsoft Excel XY chart type to display a risk matrix that shows risk probability and potential impact.

## Slide 39: Risk Management (Cont. 3)
Risk Management Software
  Assigns specific dates as constraints
  Aligns task dependencies
  Notes external factors that might affect a task
  Tracks progress
  Displays tasks that are behind schedule

## Slide 40: Managing for Success
Business Issues
  Every system is to provide a solution to a business problem or opportunity
Budget Issues
  Cost overruns result from:
      Unrealistic estimates
      Failure to develop an accurate forecast
      Poor monitoring of progress and slow response to early warning signs of problems
      Schedule delays due to unforeseen factors
      Human resource issues

## Slide 41: Managing for Success (Cont.)
Schedule Issues
  Problems with timetables and project milestones can indicate:
    Failure to recognize task dependencies
    Confusion between effort and progress
    Poor monitoring and control methods
    Personality conflicts among team members
    Turnover of project personnel
    Failure of an IT project

## Slide 42: The Bottom Line
Project managers must be alert, technically competent, and highly resourceful
Strong communication and human resource skills are necessary
When problems occur, the project manager’s ability to handle the situation becomes the critical factor

## Slide 43: Chapter Summary
Project management is the process of planning, scheduling, monitoring, and reporting on the development of an information system
  A successful project must be completed on time, within its budget, and deliver a quality product that satisfies users and meets requirements
A project triangle shows three legs that require balancing— project cost, scope, and time

## Slide 44: Chapter Summary (Cont. 1)
Planning, scheduling, monitoring, and reporting all take place within a larger project development framework, which includes three key steps—creating a work breakdown structure, identifying task patterns, and calculating the critical path
Task patterns establish the sequence of work in a project
A critical path is a series of tasks that, if delayed, would affect the completion date of the overall project

## Slide 45: Chapter Summary (Cont. 2)
A Gantt chart is a horizontal bar chart that represents the project schedule with time on the horizontal axis and tasks arranged vertically
A PERT/CPM chart shows the project as a network diagram with tasks connected by arrows
Most project managers use powerful software such as Microsoft Project to plan, schedule, and monitor projects